## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: 5 |  |  |  |  | Jordan Chen | jchen292@uic.edu
Week Of: April 22 - 26, 2019 |  |  |  |  | Bryan Nguyen | bnguye39@uic.edu
[5 empty] | Edgar Camacho | edgarc2@uic.edu
[5 empty] | Juan Guiterrez | jgutie61@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Game Logic | 1 | Juan Guiterrez | Learn Node JS and Brainstorm Game functions | Start deciding how game will be played out | Write Game Logic Code
Configuring game scenes and adding addition features | 2 | Jordan Chen | Learn Node JS and HTML | Decide how Tank will function in game | Implement the Tank in the game
Networking features and connection between server and Clients | 3 | Edgar Camacho | Learn Node JS | Start Server for Game | Configure the Server and Client Logic together and make them connect
GUI elements and Enchancing certain elements | 4 | Bryan Nguyen | Learn Node JS, HTML, and CSS | Create ideas for how the GUI and user interface will look like | Implement GUI and UI deisgns